## Module 2 - 05-31-2020
PSP Time Recording Log | [7 empty] | PSP2 Project Summary
Date | Start | Stop | Interruption Time (minutes) | Delta Time (minutes) | Phase | Comments |  | Time in Phase (minutes) | Estimated | Actual | To Date | To Date %
2020-05-25 | 8:11 | 8:55 |  | 44 | Planning |  |  | Planning | * | 204 | 204 | 9.99%
2020-05-25 | 9:31 | 10:05 |  | 34 | Planning |  |  | Design | * | 438 | 438 | 21.45%
2020-05-25 | 13:41 | 15:47 |  | 126 | Planning |  |  | Code | * | 1265 | 1265 | 61.95%
2020-05-26 | 6:14 | 8:12 | 12 | 106 | Design | Interruption: Wife went to work, made lunch for her |  | Code Review | * | 0 | 0 | 0%
2020-05-26 | 9:33 | 11:12 |  | 99 | Design |  |  | Test | * | 135 | 135 | 6.611%
2020-05-26 | 12:02 | 14:45 |  | 163 | Design |  |  | Post Mortem | * | 0 | 0 | 0%
2020-05-26 | 15:55 | 17:05 |  | 70 | Design |  |  | TOTAL | 0 | 2042 | 2042 | 100%
2020-05-26 | 19:45 | 22:15 | 9 | 141 | Code | Interruption: Phone call
2020-05-27 | 6:23 | 9:12 |  | 169 | Code
2020-05-27 | 9:33 | 10:15 | 4 | 38 | Code | Interruption: Getting coffee
2020-05-27 | 11:03 | 14:55 |  | 232 | Code |  |  | PSP2 Project Summary
2020-05-27 | 15:09 | 15:55 |  | 46 | Test |  |  | Defects Injected | Estimated | Actual | To Date | To Date %
2020-05-27 | 16:05 | 16:23 |  | 18 | Test |  |  | Planning | * | 0 | 0 | 0%
2020-05-27 | 16:24 | 18:09 |  | 105 | Code |  |  | Design | * | 8 | 8 | 16.33%
2020-05-27 | 18:23 | 18:55 | 8 | 24 | Code | Interruption: Wife went to work |  | Code | * | 22 | 22 | 44.9%
2020-05-27 | 19:01 | 20:25 |  | 84 | Code |  |  | Code Review | * | 0 | 0 | 0%
2020-05-27 | 20:25 | 20:35 |  | 10 | Test |  |  | Test | * | 19 | 19 | 38.78%
2020-05-27 | 20:45 | 21:00 |  | 15 | Test |  |  | Post Mortem | * | 0 | 0 | 0%
2020-05-27 | 21:00 | 21:48 | 11 | 37 | Code | Interruption: Bathroom break |  | TOTAL | 0 | 49 | 49 | 100%
2020-05-28 | 7:15 | 10:45 |  | 210 | Code
2020-05-28 | 11:47 | 15:45 |  | 13 | Code
2020-05-28 | 15:45 | 15:58 |  | 13 | Test |  |  | Summary
2020-05-29 | 4:23 | 6:30 | 34 | 93 | Code | Interruption: Wife went to work, made lunch for her |  |  | Estimated | Actual | To Date
2020-05-29 | 6:33 | 7:21 |  | 48 | Code |  |  | Program Size (LOC) | * | 296 | 296
2020-05-29 | 7:36 | 8:50 | 3 | 71 | Code | Interruption: Text |  | LOC/Hour | * | 8.6974 | 8.6974
2020-05-29 | 8:50 | 9:03 |  | 13 | Test |  |  | Defects/KLOC | * | 165.5405 | 165.5405
2020-05-29 | 10:45 | 11:13 | 16 | 12 | Test | Interruption: Phone call and text
2020-05-29 | 13:15 | 13:23 |  | 8 | Test
PSP Defect Recording Log
SI No: | Date | Defect Type | Defect Inject Phase | Defect Removal Phase | Fix Time (minutes) | Fix Ref | Description
1 | 2020-05-26 |  | Design | Design | 11 | n/a | Implementation of appropriate methods
2 | 2020-05-26 |  | Code | Code | 8 | n/a | Incorrect columns resulting in error
3 | 2020-05-27 |  | Code | Code | 13 | n/a | Initializing array missi
4 | 2020-05-27 |  | Code | Code | 12 | n/a | No method to check if user places < 1 or > 7
5 | 2020-05-27 |  | Test | Test | 8 | n/a | Scanner class not instantiated correctly
6 | 2020-05-27 |  | Code | Code | 22 | n/a | Incorrect code for diagonal check
7 | 2020-05-28 |  | Code | Code | 13 | n/a | Method missing for valid move
8 | 2020-05-28 |  | Code | Code | 31 | n/a | Index out of bounds, row error
9 | 2020-05-29 |  | Test | Test | 4 | n/a | Splitting of classes not recognized
10 | 2020-05-29 |  | Test | Test | 3 | n/a | Understanding the use of packages

## Module 3 - 06-07-2020
PSP Time Recording Log | [7 empty] | PSP2 Project Summary
Date | Start | Stop | Interruption Time (hh:mm:ss) | Delta Time (minutes) | Phase | Comments |  | Time in Phase (minutes) | Estimated | Actual | To Date | To Date %
2020-06-03 | 16:37 | 16:47 | 0:38 | 3 | Planning | Interruption: Text |  | Planning | 20 | 3 | 207 | 9.857%
2020-06-03 | 16:47 | 16:54 |  | 6 | Design |  |  | Design | 30 | 6 | 444 | 21.14%
2020-06-03 | 16:54 | 17:05 |  | 10 | Code |  |  | Code | 500 | 41 | 1306 | 62.19%
2020-06-03 | 17:07 | 17:38 |  | 30 | Code |  |  | Code Review | 0 | 0 | 0 | 0%
2020-06-03 | 17:38 | 17:41 |  | 2 | Test |  |  | Test | 300 | 3 | 138 | 6.571%
2020-06-03 | 17:41 | 17:42 |  | 1 | Test |  |  | Post Mortem | 10 | 5 | 5 | 0.2381%
2020-06-04 | 17:19 | 17:30 |  | 10 | Design |  |  | TOTAL | 860 | 58 | 2100 | 100%
2020-06-04 | 17:32 | 17:37 |  | 5 | Post Mortem
PSP2 Project Summary
[8 empty] | Defects Injected | Estimated | Actual | To Date | To Date %
[8 empty] | Planning | 0 | 0 | 0 | 0%
[8 empty] | Design | 10 | 0 | 8 | 16.33%
[8 empty] | Code | 100 | 0 | 22 | 44.9%
[8 empty] | Code Review | 20 | 0 | 0 | 0%
[8 empty] | Test | 20 | 0 | 19 | 38.78%
[8 empty] | Post Mortem | 0 | 0 | 0 | 0%
[8 empty] | TOTAL | 150 | 0 | 49 | 100%
Summary
[9 empty] | Estimated | Actual | To Date
[8 empty] | Program Size (LOC) | 200 | 109 | 405
[8 empty] | LOC/Hour | 30 | 112.7586 | 11.5714
[8 empty] | Defects/KLOC | 10 | 0 | 120.9877
PSP Defect Recording Log
SI No: | Date | Defect Type | Defect Inject Phase | Defect Removal Phase | Fix Time (minutes) | Fix Ref | Description

## Module 4 - 06-14-2020
PSP Time Recording Log | [7 empty] | PSP2 Project Summary
Date | Start | Stop | Interruption Time | Delta Time (minutes) | Phase | Comments |  | Time in Phase (minutes) | Estimated | Actual | To Date | To Date %
2020-06-09 | 13:49 | 13:53 | n/a | 4 | Test | Removal of @NotNull instances |  | Planning | 120 | 167 | 374 | 11.22%
2020-06-09 | 14:10 | 14:17 | n/a | 6 | Test | Fix of non-numeric character input result in program crashing. |  | Design | 60 | 52 | 496 | 14.88%
2020-06-09 | 14:17 | 14:19 | n/a | 2 | Test | PvsC game should start for only selecting C or c as user input, but PvsC game starts for other characters, e.g. r, t, g etc. Fix this issue, otherwise, marks will be deducted in the future. - Fix |  | Code | 600 | 898 | 2204 | 66.13%
2020-06-09 | 14:19 | 15:17 | n/a | 57 | Test | For the PvsP game, a player's turn switches to another player if that player wants to select a column which is already filled. - Fix |  | Code Review | 120 | 13 | 13 | 0.39%
2020-06-09 | 15:17 | 15:30 | n/a | 13 | Code | Create method to handle tie |  | Test | 120 | 92 | 230 | 6.901%
2020-06-09 | 15:30 | 15:47 | n/a | 17 | Test | PvsC game should start for only selecting C or c as user input, but PvsC game starts for other characters, e.g. r, t, g etc. Fix this issue, otherwise, marks will be deducted in the future. - Fix |  | Post Mortem | 60 | 11 | 16 | 0.48%
2020-06-09 | 15:52 | 17:17 | n/a | 84 | Plan | Planning for Module 4 |  | TOTAL | 1080 | 1233 | 3333 | 100%
2020-06-09 | 19:28 | 19:29 | n/a | 1 | Plan | Planning for Module 4
2020-06-10 | 7:28 | 8:22 | n/a | 56 | Plan | Planning for Module 4
2020-06-10 | 8:26 | 8:41 | n/a | 14 | Plan | Planning for Module 4
2020-06-10 | 8:42 | 9:06 | n/a | 24 | Code | Coding GUI |  | PSP2 Project Summary
2020-06-10 | 9:18 | 9:30 | n/a | 12 | Code | Coding GUI |  | Defects Injected | Estimated | Actual | To Date | To Date %
2020-06-10 | 11:11 | 0:47 | n/a | 96 | Code | Coding GUI |  | Planning | 0 | 0 | 0 | 0%
2020-06-10 | 13:03 | 14:51 | n/a | 108 | Code | Coding GUI |  | Design | 10 | 0 | 8 | 14.81%
2020-06-10 | 15:20 | 15:29 | n/a | 9 | Code | Coding GUI |  | Code | 100 | 1 | 23 | 42.59%
2020-06-10 | 15:33 | 15:45 | n/a | 12 | Plan | Planning for Module 4 |  | Code Review | 20 | 0 | 0 | 0%
2020-06-10 | 15:46 | 15:53 | n/a | 7 | Code | Coding GUI |  | Test | 20 | 4 | 23 | 42.59%
2020-06-10 | 16:24 | 17:04 | n/a | 40 | Code | Coding GUI |  | Post Mortem | 0 | 0 | 0 | 0%
2020-06-10 | 17:48 | 18:33 | n/a | 45 | Code | Coding GUI |  | TOTAL | 150 | 5 | 54 | 100%
2020-06-10 | 18:49 | 19:12 | n/a | 24 | Code | Coding GUI
2020-06-11 | 8:36 | 14:23 | n/a | 347 | Code | Coding GUI
2020-06-11 | 15:00 | 16:38 | n/a | 98 | Code | Coding GUI |  | Summary
2020-06-11 | 16:45 | 16:47 | n/a | 1 | Code | Coding GUI |  |  | Estimated | Actual | To Date
2020-06-13 | 8:24 | 9:39 | n/a | 74 | Code | Coding GUI |  | Program Size (LOC) | 200 | 559 | 964
2020-06-13 | 9:40 | 9:46 | n/a | 6 | Test | Testing application |  | LOC/Hour | 30 | 27.2019 | 17.3537
2020-06-13 | 9:46 | 10:39 | n/a | 52 | Design | Finishing designing of UML |  | Defects/KLOC | 10 | 8.9445 | 56.0166
2020-06-13 | 10:39 | 10:53 | n/a | 13 | Code Review | Code Review
2020-06-13 | 10:53 | 11:04 | n/a | 11 | Post Mortem | Post Mortem
PSP Defect Recording Log
SI No: | Date | Defect Type | Defect Inject Phase | Defect Removal Phase | Fix Time (minutes) | Fix Ref | Description
1 | 2020-06-09 | 30 | Test | Test | 3 | n/a | Removal of @NotNull
2 | 2020-06-09 | 80 | Test | Test | 6 | n/a | Fix of non-numeric character input resulting in program crashing
3 | 2020-06-09 | 80 | Test | Test | 20 | n/a | PvsC game should start for only selecting C or c as user input, but PvsC game starts for other characters, e.g. r, t, g etc. Fix this issue, otherwise, marks will be deducted in the future. - Fix
4 | 2020-06-09 | 80 | Test | Test | 57 | n/a | For the PvsP game, a player's turn switches to another player if that player wants to select a column which is already filled. - Fix
5 | 2020-06-11 | 80 | Coding | Coding | 30 | n/a | Reset button does not work. I am not sure how to reset the GridPane

## Module 5 - 06-21-2020
PSP Time Recording Log | [7 empty] | PSP2 Project Summary
Date | Start | Stop | Interruption Time | Delta Time (minutes) | Phase | Comments |  | Time in Phase (minutes) | Estimated | Actual | To Date | To Date %
[8 empty] | Planning | 0 | 0 | 374 | 11.22%
[8 empty] | Design | 0 | 0 | 496 | 14.88%
[8 empty] | Code | 0 | 0 | 2204 | 66.13%
[8 empty] | Code Review | 0 | 0 | 13 | 0.39%
[8 empty] | Test | 0 | 0 | 230 | 6.901%
[8 empty] | Post Mortem | 0 | 0 | 16 | 0.48%
[8 empty] | TOTAL | 0 | 0 | 3333 | 100%
PSP2 Project Summary
[8 empty] | Defects Injected | Estimated | Actual | To Date | To Date %
[8 empty] | Planning | 0 | 0 | 0 | 0%
[8 empty] | Design | 0 | 0 | 8 | 14.81%
[8 empty] | Code | 0 | 0 | 23 | 42.59%
[8 empty] | Code Review | 0 | 0 | 0 | 0%
[8 empty] | Test | 0 | 0 | 23 | 42.59%
[8 empty] | Post Mortem | 0 | 0 | 0 | 0%
[8 empty] | TOTAL | 0 | 0 | 54 | 100%
Summary
[9 empty] | Estimated | Actual | To Date
[8 empty] | Program Size (LOC) | 200 |  | 964
[8 empty] | LOC/Hour | 30 | #DIV/0! | 17.3537
[8 empty] | Defects/KLOC | 10 | #DIV/0! | 56.0166
PSP Defect Recording Log
SI No: | Date | Defect Type | Defect Inject Phase | Defect Removal Phase | Fix Time (minutes) | Fix Ref | Description